## Format
SEDEMAC |  | Process Compliance Metric For : GC2X-GC2111-RA6M2 R6 |  | Doc # |  | SW-Process Compliance Metric-GC2X-GC2111-RA6M2
|  |  |  | Rev # / Rev Date |  | 0.01 / 08-06-2023 |  |  |  | None | Often | No
|  |  |  | Page # |  | 1 of 1 |  |  |  | Occasionally | Few times | Yes
SW team members: |  | SuryaPranayTeja | [5 empty] | Not done | Not done | Partly | Very rarely
SW Project Leader (PL): |  | Pramod Ranade | [5 empty] | Not applicable | Done | Mostly | Never
Filled metric reviewed and approved by: | [7 empty] | Done |  | Fully
Any other information: |  | The Metric is filled only for the changes made from its previous release.(Bug fix of Invalid DG Run and Modbus issue)
Source code details of software subjected to test: |  | BitBucket Project: | SW - GC2X
|  | APL Repository: | gc2111_renesas
|  | APL Branch: | GC2111_RA6M2
|  | APL Commit ID: | eb2e128
|  | BSP Repository: | gc2k-bsp
|  | BSP Branch: | GC2111_BSP
|  | BSP Commit ID: | ceb63ae
# | Process step / item |  | Status | Weight | Score | Remark | Weight'
1 | SRS (for new SW development work) or "change request / bug report" (for SW modification work) received from customer? |  | Not done | 1 | 0 |  | 1
2 | SRS uploaded in "docs" folder in Bitbucket repository of project OR change request(s) and/or bug report(s) added in JIRA (whichever of these two is applicable). |  | Not done | 1 | 0 |  | 1
3 | SRS (or change request) is reviewed by PL and confirmed that it is feasible (i.e. feasibility confirmation sent to customer)? |  | Not applicable | 1 | 0 | Since there is no change in SRS from NXP to Renesas controller change | 0
4 | SW Project plan is in place?1 |  | Not applicable | 1 | 0 |  | 0
5 | Milestones and expected completion dates updated in project plan (possibly via SYSE)2 |  | Not applicable | 1 | 0 |  | 0
6 | SW SRS created (based on the received SRS)?1 |  | Not applicable | 2 | 0 | Not created /required as the change is only Microcontroller porting. | 0
7 | SW SRS is reviewed and approved by concerned Engineer from SYSE?3 Write name of SYSE Engineer in Remark column. |  | Not applicable | 1 | 0 | Not created /required as the change is only Microcontroller porting. | 0
8 | SW SRS is as per defined format (QF-01)?3 |  | Not applicable | 1 | 0 | SRS is found in NXP repository and same. | 0
9 | SW SRS filename and document name matches naming convention (QP-03)?3 |  | Not applicable | 1 | 0 | SRS is found in NXP repository and same. | 0
10 | SW SRS reviewed and approved by Chief Engineer?3 |  | Not applicable | 1 | 0 | SRS is found in NXP repository and same. | 0
11 | SW SRS uploaded in "docs" folder in Bitbucket repository of the project?3 |  | Not applicable | 1 | 0 | SRS is found in NXP repository and added to renesas repo later | 0
12 | Has the SW team referred to "Lessons learnt" - i.e. the two confluence pages: Common Errors and More Coding Guidelines. |  | Done | 1 | 1 | Lessons Learnt are referred from the Google Sheet | 1
13 | SDD created?1 |  | Not applicable | 3 | 0 |  | 0
14 | SDD is as per defined format (QF-02)?4 |  | Not applicable | 1 | 0 |  | 0
15 | SDD filename and document name matches naming convention (QP-03)?4 |  | Not applicable | 1 | 0 |  | 0
16 | SDD is reviewed and approved by Chief Engineer?4 |  | Not applicable | 1 | 0 |  | 0
17 | SDD uploaded in "docs" folder in Bitbucket repository of the project?4 |  | Not applicable | 1 | 0 |  | 0
18 | Bitbucket repository for the project created? |  | Done | 3 | 3 |  | 3
19 | Bitbucket repository and Bitbucket project names are as per naming convention (QP-02)? |  | Done | 1 | 1 |  | 1
20 | Branches "master" and "develop" created? |  | Done | 1 | 1 |  | 1
21 | Branch permissions set such that "master" and "develop" can be updated only by PL? |  | Done | 1 | 1 |  | 1
22 | Git branches as per QP-06 are in use? |  | Not done | 1 | 0 |  | 1
23 | Unit test plan is created for how many units (write answer in "Status" column)? How many units actually need unit testing (write answer in "Remark" column)? |  | 0 | 3 | 0 | 0 | 3
24 | Number of "all ok" unit test reports (write answer in "Status" column)? |  | 0 | 3 | 0 | 0 | 3
25 | Integration test plan created? |  | Not done | 3 | 0 |  | 3
26 | System test plan created and / or approved by concerned Engineer from SYSE?5 Write name of SYSE Engineer in Remark column. |  | Done | 3 | 3 | The Test reports are prepared for each revision and shared to Devendra for review. | 3
27 | If system testing is done partially: is this approved by Principal Engineer or Chief Engineer? |  | Done | 2 | 2 |  | 2
28 | Integration test report is "all ok"? |  | Not done | 3 | 0 |  | 3
29 | System test report is "all ok"? |  | Done | 3 | 3 | 3,4 issues are failed but deferred and consider for improvement later. Issues logged on JIRA. | 3
30 | ALL Issues discovered during Integration testing and System testing are logged in JIRA? |  | Done | 2 | 2 | All the issues are logged/reported via JIRA | 2
31 | Static Analysis run on entire source code (after integration)? Write names of tools used in "Remark" column. |  | Not done | 2 | 0 |  | 2
32 | ALL static analysis reports are closed and uploaded in "docs" folder? |  | Not done | 2 | 0 |  | 2
33 | Code review performed on entire source code (after integrsation)? Write names of reviewers in "Remark" column, |  | Done | 3 | 3 | Code Review completed for the diff and actions taken. | 3
34 | ALL code review reports are closed and uploaded in "docs" folder? |  | Not done | 3 | 0 |  | 3
35 | If any other documents are created (other than those mentioned above) then all those are uploaded in "docs" folder? Write names of all these extra documents in "Remark" column. |  | Not applicable | 1 | 0 |  | 0
36 | Written "approval for release" received from customer? |  | Done | 1 | 1 | Approved by Devendra Deshmukh | 1
37 | All branches merged into "develop"? |  | Not done | 1 | 0 |  | 1
38 | "develop" merged into "master"? |  | Not done | 1 | 0 |  | 1
39 | Code from "master" branch (after the above release) is being released? |  | Not done | 1 | 0 |  | 1
40 | Release note prepared and uploaded in "docs" folder OR Release.md in Bitbucket repository is updated. |  | Not done | 1 | 0 | Release Note is prepared but not uploaded in docs folder. Added later to the repo. | 1
41 | Naming convention (as per QP-05) for identifiers and files is followed?6 |  | Mostly | 4 | 3 |  | 4
42 | Magic numbers used?6 |  | Very rarely | 3 | 2 |  | 3
43 | Are there compiler warnings (in the code that we have written) that can be removed?6 |  | No | 1 | 1 |  | 1
44 | Are comments written in code for each warning that cannot be removed?6 |  | Yes | 1 | 1 |  | 1
45 | Code written is modular?6 |  | Yes | 1 | 1 |  | 1
46 | Lessons learnt updated? Write about major updates in "Remark" column |  | Not done | 1 | 0 | Common Issues which needs to fixed in other products including GC2111 are listed in the firmware Issues sheet during the development | 1
[5 empty] | 29 |  | 58
|  | Percentage compliance: | 50
Notes:
1 | This item can be "Not applicable" only in case of bug report or change request.
2 | This can be "Not applicable" only if Project plan is "Not applicable".
3 | This can be "Not applicable" only if SW SRS is "Not applicable".
4 | This can be "Not applicable" only if SDD is "Not applicable".
5 | Either SW PL shall create System Test Plan and concerned SYSE Engineer shall approve it; OR concerned SYSE Engineer shall create it.
6 | In case of modifications in legacy code: this item should be evaluated w.r.t. modified code only.
|  | This format prepared by: | Pramod Ranade, Chief Engineer
|  | Reviewed and approved by: | Ajit Natu, Principal Engineer
|  | Format Rev # / Rev Date: | 2 / 14-Jan-2019