## Plan
SEDEMAC |  | Project Plan for: KG640 R3 (RA6M2) | Doc # | SW-ProjectPlan-GC1X-KG640
|  |  | Rev # / Rev Date | 3.00 / 16-Nov-2021
|  |  | Page # | 1 of 2
SW Project Leader | Name | Designation
SW Project team: | Madhuri Abhang | Principal Engg.
| Nikhil M | Engineer
| Vidhya B | Engineer
| Vikas Gore | Engineer
| Saurabh Kulkarni | Engineer
| Prachi Kulkarni | Engineer
| Ashwini Deo | Engineer
| Neeraj Abhyankar | Engineer
| Amol Supekar | Engineer
SYSE Leader | Sudeep S | Chief Engg
HW Leader | Chandrakant Patel | Principal Engg.
SW Principal Engineer | Madhuri Abhang | Principal Engineer
SW Supervisor | Pramod Ranade | Chief Engg.
Abbreviation | Role
SWPL | SW Project Leader
SWE | SW Project Team Member
SYL | SYSE Leader
HWL | HW Leader
SWPE | "Principal Engineer" from SW team, if any is assigned.
SV | SW Supervisor
Note on C5: Author: Write name and designation of SW Project Leader.
Note on C6: Author: Write names and designations of SW team members.
Note on C16: Author: Name and designation of Project Leader from SYSE division.
Note on C18: Author: Name and designation of Project Leader from HW division.
Note on C22: Author: Same as SW Principal Engineer (if assigned) or Chief Engineer

## Milestones
SEDEMAC |  | Project Plan for: GCKG640 R3 (RA6M2) |  |  |  | Doc # | SW-ProjectPlan-GC1X-KG640
[6 empty] | Rev # / Rev Date | 3.0 / 16-Nov-2021
[6 empty] | Page # | 2 of 2
Revision history: This shows how Project End Date was postponed again and again…
| Revision number (latest first) |  | Project End Date | Approved by | Date of approval | What has changed:
| V1 |  | 30th Aug 2021 | Sudeep S | 2021-04-30 | Initial Draft
| V2 |  | 30th Sep 2021 | Sudeep S | 2021-08-15 | Due to MK22 controller modificaion activity this project was postponed by 1 Month
| V3 |  | 30th Oct 2021 | Sudeep S | 2021-09-15 | Due to other porject delivery pressure, and customer Modification, this project delivary date was postponed
Milestones:
Sr. No. | Milestone |  | ETA | Actual date of reaching milestone | Remarks
1 | SRS approved by customer |  | 2021-04-26 | 2021-07-20
2 | SW SRS prepared |  | 2021-04-26 | 2021-09-23
3 | SW SRS reviewed and approved by SV |  | 2021-05-14 | 2021-09-23
4 | SDD prepared |  | 2021-09-25 | 2021-10-01
5 | SDD reviewed and approved by SV |  | 2021-10-01 | 2021-10-06
6 | BSP Development |  | 2021-06-10 | 2021-06-16
7 | HAL Development |  | 2021-07-15 | 2021-07-15
8 | Application Development |  | 2021-10-08 | 2021-10-06
9 | Logic for Event log storage |  | 2021-08-10 | 2021-08-17
10 | Integration Test Plan created |  | 2021-08-24 | 2021-08-24
11 | Integration Test Plan reviewed and approved by PL |  | 2021-08-24 | 2021-08-24
12 | Modules integrated and integration testing done successfully |  | 2021-07-25 | 2021-07-27
13 | Static Analysis done and report generated |  | 2021-09-07 | 2021-09-07
14 | Static Analysis report closed |  | 2021-10-02 | 2021-10-12
15 | Code Review done and report generated |  | 2021-08-29 | 2021-08-29
16 | Code Review Report closed |  | 2021-09-30 | 2021-09-30
17 | System Test Plan created |  | 2021-08-10 | 2021-08-10
18 | System Test Plan reviewed and approved by SYL and SV |  | 2021-08-12 | 2021-08-12
19 | System Testing done and all tests passed |  | 2021-10-15 | 2021-10-20
20 | Customer approved SW for production release |  | 2021-10-25 | 2021-11-03
21 | Software released for production |  | 2021-10-18 | 2021-10-17
| On-time? | On time!
Notes:
| 1 | You may insert more rows in the "Milestones" table above.
| 2 | You may make multiple copies of some milestones as necessary.
| 3 | You may invent new milestones as appropriate and add to the list.
| 4 | You may NOT delete any of the milestones above. If it is not applicable to your project, you may just mention "NA" in the ETA column.
Note on D5: Mention date in dd-Mmm-yyyy format
Note on E5: Should be approved by SV
Note on F5: Mention date in dd-Mmm-yyyy format
Note on D11: - This is estimated "Project End Date" - Mention date in dd-Mmm-yyyy format
Note on E11: Mention date in dd-Mmm-yyyy format
Note on C35: Author: Formula here; do not edit.