## Format
SEDEMAC |  | Software Quality Metric For : GC2115 R1 (Firmware : R0.27) |  | Doc # |  | SW-SQM-GC2115-R1 |  |  |  |  | SA tool was run, but not all warnings could be eliminated
|  |  |  | Rev # / Rev Date |  | 01 / 24-06-2024 |  |  | None | Often | No | SRS | Checked with tool and code is fully compliant
|  |  |  | Page # |  | 1 of 1 |  |  | Occasionally | Few times | Yes | JIRA Ticket(s) | By Code Review, and code is fully compliant
SW team members: |  | Aditya Joshi |  |  |  |  | Not done | Not done | Partly | Very rarely | Not Applicable | In email(s) | Checked with tool but code is NOT fully compliant
SW Project Leader (PL): |  | Soujanya Mulik |  |  |  |  | Not applicable | Done | Mostly | Never |  | In Teams message(s) | By Code Review, but code is NOT fully compliant
SQM filled by: |  | Aditya Joshi |  |  |  |  | Done |  | Fully |  |  | Not documented | Not checked
SQM approved by: |  | Soujanya Mulik
Any other information:
Source code details of software subjected to test: |  | BitBucket Project: | SW_GC2X_NEW |  | BitBucket Project: | SW_GC2X
|  | Repository: | mnm_gc2115 |  | Repository: | gc2k-bsp
|  | Branch: | release/mnm-0.27 |  | Branch: | improvement/STB_fault_detection
|  | Commit ID: | 36c97b6 |  | Commit ID: | 963ba8a
# | Question |  | Answer |  | Score | Remark | [7 empty] | Scoring rule explaination
1 | How is the requirement documented? |  | JIRA Ticket(s) |  | 4 | https://sedemac.atlassian.net/jira/software/c/projects/GC2115/issues | [7 empty] | SRS, Jira, Email, Teams message have 5, 4, 3, 2 marks respectively. 0 otherwise.
2 | How well is the requirement documented: what is the percentage of requirements covered in the documentation? |  | 100 |  | 8 | [8 empty] | If < 60%: 0 score. Otherwise take the same percentage of the score of previous question and multiply it by 2.
3 | Are we going to satisfy ALL the requirements? |  | Yes
4 | If not: have we informed the customer by written communication that we will not implement some of the requirements (including the list of requirements that we will not implement)? |  | No
5 | In continuation with previous question: have we received confirmation from customer (by written communication) that they can accept the software even if we do not implement the specified requirements? |  | No |  | 10 | [8 empty] | If requirement is NOT documented: 0. Otherwise, if we are going to satisfy ALL requirements: 10. Otherwise, if customer has approved partial requirement implementation: 10. Otherwise: 0
6 | Is Software Architecture showing Software Components and Layers documented? |  | Yes |  | 2 | High Level Design | [7 empty] | Yes = 2; No = 0.
7 | In continuation with previous question: is it reviewed by someone other than the author AND all comments have been acted upon and closed to the satisfaction of the reviewer? |  | Yes |  | 2 | Reviewed by Ramachandran S | [7 empty] | If answer to this question AND previous question is "Yes", then 2. Otherwise 0.
8 | Is Interrupt documentation available (list of ALL enabled interrupts, their priorities, their estimated execution time and estimated CPU load %, their actual (measured) execution time and CPU load %) |  | No |  | 0 | [8 empty] | Yes = 2; No = 0.
9 | In continuation with previous question: is it reviewed by someone other than the author AND all comments have been acted upon and closed to the satisfaction of the reviewer? |  | No |  | 0 | [8 empty] | If answer to this question AND previous question is "Yes", then 2. Otherwise 0.
10 | Is Memory map sheet available indicating memory size, usage, free space, their address ranges etc (for ALL types of memories - like PFlash, DFlash, RAM, EEPROM etc) |  | Yes |  | 2 | Memory Map | [7 empty] | Yes = 2; No = 0.
11 | In continuation with previous question: is it reviewed by someone other than the author AND all comments have been acted upon and closed to the satisfaction of the reviewer? |  | Yes |  | 2 | Reviewed by Ramachandran S | [7 empty] | If answer to this question AND previous question is "Yes", then 2. Otherwise 0.
12 | Is CAN ID usage documented indicating all CAN IDs used by this ECU and other ECUs in the system? |  | Yes |  | 1 | J1939 MAP | [7 empty] | Yes = 1; Not Applicable = 0.5; No = 0.
13 | In continuation with previous question: is it reviewed by someone other than the author AND all comments have been acted upon and closed to the satisfaction of the reviewer? |  | Yes |  | 1 | Reviewed by Rahul Hage from SysE. | [7 empty] | If answer to this question AND previous question is "Yes", then 1. Otherwise 0.
14 | State machine diagrams (of important state machines) documented? |  | No |  | 0 | [8 empty] | Yes = 1; Not Applicable = 0.5; No = 0.
15 | In continuation with previous question: is it reviewed by someone other than the author AND all comments have been acted upon and closed to the satisfaction of the reviewer? |  | No |  | 0 | [8 empty] | If answer to this question AND previous question is "Yes", then 1. Otherwise 0.
16 | Flowcharts or algorithms (for important and / or complex functionality) documented? |  | Yes |  | 1 | Confluence Page | [7 empty] | Yes = 1; Not Applicable = 0.5; No = 0.
17 | In continuation with previous question: is it reviewed by someone other than the author AND all comments have been acted upon and closed to the satisfaction of the reviewer? |  | No |  | 0 | [8 empty] | If answer to this question AND previous question is "Yes", then 1. Otherwise 0.
18 | Communication protocols documented? |  | Yes |  | 1 | MODBUS MAP has been attched in the test report | [7 empty] | Yes = 1; Not Applicable = 0.5; No = 0.
19 | In continuation with previous question: is it reviewed by someone other than the author AND all comments have been acted upon and closed to the satisfaction of the reviewer? |  | Yes |  | 1 | Reviewed by Rahul Hage[SYSE] | [7 empty] | If answer to this question AND previous question is "Yes", then 1. Otherwise 0.
20 | How is compliance with Coding Guidelines checked? |  | By Code Review, and code is fully compliant |  | 4 | [8 empty] | Score = 5 / 4 / 3 / 2 for the first 4 options respectively. Score = 0 if "Not checked"
21 | Code review was done and all comments acted upon and closed to the satisfaction of the reviewer? |  | Yes |  | 10 | Code reviewers: Ramachandran S Soujanya M | [7 empty] | 10 marks only if Code Review done and all comments acted on.
22 | Static Analysis tool was run and all warnings eliminated? |  | No |  | 0 | [8 empty] | 0 marks if SA done. 1 mark if SA done, but not all warnings eiminated. 2 marks if SA done and all warnings eliminated.
23 | All compiler warnings eliminated? |  | No |  | 0 | 11 warnings | [7 empty] | 3 if Yes, 0 otherwise.
24 | Test Cases were created / updated? |  | Yes |  | 5 | Test cases updated by : Upendra K. | [7 empty] | 5 if Yes, 0 otherwise.
25 | Is Test Report available for any intermediate software version? |  | Yes |  | 5 | Test reports of R0v03, R0v08 and R0v20 are available in OHA+OHSW Teams chat | [7 empty] | 5 if Yes, 0 otherwise.
26 | Is Test Report available for final software version (which is to be released for production)? |  | Yes |  | 10 | Test Reports | [7 empty] | 10 if Yes, 0 otherwise.
27 | Has customer approved (in writing) the release of the same version of software? |  | Yes |  | 9 | Release request received from Rahul Hage[SYSE] over Teams | [7 empty] | 9 if Yes, 0 otherwise.
28 | Is the software being delivered (released) on time? |  | Yes |  | 1 | [8 empty] | 1 if Yes, 0 otherwise.
29 | If not, how much was the delay in weeks? |  | 0 |  | 1 | [8 empty] | 0 if delay > 1 week; 1 otherwise.
30 | Has the SW team referred to "Lessons learnt" - i.e. the Confluence page "Lessons Learnt" and all of it's child pages, including "Common Errors", "More Coding Guidelines" and other bug reports (sorted by year)? |  | No |  | 0 | [8 empty] | 1 if Yes, 0 otherwise.
31 | Bitbucket repository for the project created? |  | Yes |  | 1 | [8 empty] | 1 if Yes, 0 otherwise.
32 | Bitbucket repository and Bitbucket project names are as per naming convention (QP-02)? |  | Yes |  | 1 | [8 empty] | 1 if Yes, 0 otherwise.
33 | Branches "master" and "develop" created? |  | Yes |  | 1 | [8 empty] | 1 if Yes, 0 otherwise.
34 | Branch permissions set such that "master" and "develop" can be updated only by PL? |  | Yes |  | 1 | [8 empty] | 1 if Yes, 0 otherwise.
35 | Git branches as per QP-06 are in use? |  | Yes |  | 1 | [8 empty] | 1 if Yes, 0 otherwise.
36 | All branches merged into "develop"? |  | Yes |  | 1 | [8 empty] | 1 if Yes, 0 otherwise.
37 | "develop" merged into "master"? |  | Yes |  | 1 | [8 empty] | 1 if Yes, 0 otherwise.
38 | Code from "master" branch (after the above release) is being released? |  | Yes |  | 1 | [8 empty] | 1 if Yes, 0 otherwise.
39 | Release note prepared and uploaded in "docs" folder OR Release.md in Bitbucket repository is updated. |  | Yes |  | 1 | [8 empty] | 1 if Yes, 0 otherwise.
40 | Lessons learnt updated? Write about major updates in "Remark" column |  | No |  | 0 | [8 empty] | 1 if Yes, 0 otherwise.
83
|  | Software Quality score: | 83
|  | This format prepared by: | Pramod Ranade, Chief Engineer
|  | Reviewed and approved by: | Sandesh Achari, Principal Engineer
|  | Format Rev # / Rev Date: | 3 / 8-Jun-2023
Note on A5: Quality Reviewer must fill this metric sheet.
Note on A6: Quality Reviewer must fill this metric sheet, together with the PL. Some information maybe filled by the PL in advance (e.g. the header, source code details etc) Quality Reviewer must be someone who: 1. Is a SW Development team member but not part of this project team. 2. Has designation Lead Engineer or Principal Engineer or Chief Engineer.
Note on A7: SQM should be approved by someone who: 1. Is a SW Development team member but not part of this project team. 2. Has designation Principal Engineer or Chief Engineer. 3. Should not be the same person who filled this SQM.
Note on G20: Write here "where". i.e. Name of and link to Confluence page, document or XLS sheet in repository or Google doc or sheet etc.
Note on G22: Write here "where". i.e. Name of and link to Confluence page, document or XLS sheet in repository or Google doc or sheet etc.
Note on G24: Write here "where". i.e. Name of and link to Confluence page, document or XLS sheet in repository or Google doc or sheet etc.
Note on G26: Write here "where". i.e. Name of and link to Confluence page, document or XLS sheet in repository or Google doc or sheet etc. OR Write why this is N.A.
Note on G28: Write here "where". i.e. Name of and link to Confluence page, document or XLS sheet in repository or Google doc or sheet etc. OR Write why this is N.A.
Note on G30: Write here "where". i.e. Name of and link to Confluence page, document or XLS sheet in repository or Google doc or sheet etc. OR Write why this is N.A.
Note on G32: Write here "where". i.e. Name of and link to Confluence page, document or XLS sheet in repository or Google doc or sheet etc. OR Write why this is N.A.
Note on G35: Author: Write name(s) of Code Reviewer(s) here.
Note on B36: Author: Warnings due to tool generated code are acceptable.
Note on B37: Author: Warnings due to tool generated code are acceptable.
Note on G38: Author: Who created / updated the Test Cases? Write name here.
Note on B40: Author: Test Report must have this information: Who tested? When? What was the version of software tested? Source code details? What test setup was used? Summary: how many test cases were performed? How many passed? Percentage? etc.
Note on G42: Author: Write here the definition of "on time". And how "delay" is measured, in case of delayed releases.